## 1. Intro
Monitoring Framework Tool
Purpose of this document
This is a tool to support the development of a monitoring framework.
What are the goals of monitoring?
1 | Deliver a better project
Good monitoring can directly improve the delivery of a project. At its best, monitoring serves as a feedback loop that directly informs decision-making throughout a project. It is not an activity done in parallel to programme delivery, it is part of delivery itself.
Monitoring can do this by creating formal checkpoints for the team to pause, pay attention to key questions, collect information and have conversations in answer to those questions, and then make programmatic course corrections as a result. Each monitoring question should have a clear purpose that the team thinks will help them achieve the objectives of the project. Monitoring should not just become a box-ticking exercise that consumes scarce time.
2 | Learning
Monitoring can lead to multiple kinds of learning. Monitoring questions can push the team to examine their work more closely, and therefore help the team learn whether a certain approach is working.
Monitoring data can feed into evaluation exercises of the project.
3 | Accountability
Any reporting requirements should be kept in mind when designing the monitoring database so that the data captured in response to the monitoring questions will facilitate reporting.
Components of this document
1 | Introduction
This first tab provides a definition of monitoring and outlines its main purposes. It also provides an overview of the structure of this document.
2 | Overarching questions and ToC
The second tab in this document presents the high-level (overarching) questions that underpin each of the main sections of the theory of change (i.e. input/resources, activities, outputs, outcomes, enablers/critical factors). These overarching questions are meant to guide the development of more specific monitoring questions that will require specific data to answer. Please note that you must have a theory of change to use the monitoring framework tool.
3 | Monitoring universe
The third tab in this document presents a comprehensive breakdown of the universe of the possible monitoring questions, data sources and indicators that could in theory be targeted by the project monitoring in order to probe each of the components of the theory of change and guide any implementation adaptations, as well as provide data and insights for an eventual evaluation of the impact of the project.
It is often not possible or practical to pursue all the monitoring questions so strategic decision must be made regarding the key questions that will be the focus of the monitoring activities.
4 | Monitoring plan
The fourth tab in this document consists of the monitoring plan and database for the project. It contains only the key questions selected from the monitoring universe as the questions that will be the focus of all monitoring activities.
The monitoring plan specifies the data source (where the data will come from) as well as the indicators (the data points that will be analysed) to be used to answer the key questions.
The monitoring plan also identifies the person responsible for the monitoring activities associated with each question, along with the frequency of monitoring.
Finally, the tab can be used as a database where the monitoring data is recorded according to the frequency specified. This enables all monitoring data to be stored in one location, facilitating its analysis and eventually reporting.
5 | Data Sources
The final tab has a list of (eventually) finalised data sources and the target group. It is also useful for assessing the feasibility of the monitoring plan.

## 2. Overarching Questions & ToC
Overarching Questions and Theory of Change
This list of questions represents the high-level monitoring questions that will support the design of this monitoring database by providing the team with a shared reference point to ensure data is captured on all the different things that should be monitored for the project. These high-level (overarching) questions underpin each of the main sections of the theory of change (i.e. input/resources, activities, outputs, outcomes, enablers/critical factors) and are meant to guide the development of more specific monitoring questions that will require specific data to answer in the next tabs of this tool. Please note that you must have a theory of change to use the monitoring framework tool. Here we include, as an example, a theory of change from the Dignitas project "Lead Now" (https://leadnow.dignitasproject.org/). Dignitas' LeadNow app is a tech tool to support the remote coaching of school leaders and enhance school-based teacher development in Kenya. This app is embedded in Dignitas’ digital training and coaching toolkit LeadNow, designed for and by School Leaders. When using this tool, you can replace this example theory of change with your own, by deleting this one and pasting your own in its place.
Overarching monitoring questions | Which relevant section(s) of the theory of change?
| Inputs/ Activities | Ouputs | Outcomes | Goals | Critical factors / enablers
Is the workplan realistic in terms of budget and staff time? | ✓
Are activities happening as planned? | ✓
Are activities leading to the expected outputs? | ✓ | ✓
Are activities leading to the expected outcomes? | ✓ |  | ✓
Are the short-term outcomes leading to the expected goals? |  |  | ✓ | ✓
Are the enabling factors in place? Are there derailing factors? |  |  |  |  | ✓
How does the changing context affect our workplan? Should the workplan be changed according to changes in context? |  |  |  |  | ✓
For example, see the Theory of Change by Dignitas below.

## 3. Monitoring Universe
Monitoring Universe
What could we measure?
| Theory of Change | Monitoring Questions | Purpose / Rationale | Transition to Monitoring Plan: Is answering the MEL question…. |  |  |  | Decision: Should we prioritise this monitoring question and include it in our Monitoring Plan?
Overarching Questions | Add all statements from the theory of change (excluding the goals beyond the accountability line) | What do we want to reflect upon? | Why are we asking this question? | ...a strategic priority (something that is important to us)? | ...a reporting requirement (from funders, partners, etc.)? | ...feasible? | … practical?
Activities
Are activities happening as planned?
Mechanisms for Change
Are activities happening as planned?
Enabling Factors
Are the enabling factors in place?
Outputs
Are activities leading to the expected outputs?
Outcomes
Are activities leading to the expected outcomes?
Goals
Are the outcomes leading to the expected goals?
Note: Goals beyond the accountability line are not included in the monitoring universe.

## 4. Monitoring Plan
Monitoring Plan
What do we plan to measure?
Theory of Change | Monitoring Questions | Purpose / Rationale | Success Criteria | Data Sources | Indicators | Timing / Frequency | Owner | Starting Point / Baseline | Note: The columns to the right can be used as a database to record the data for each monitoring question and according to the timing/frequency indicated.
Add the elements from the ToC that you have decided to monitor (as per the priority exercise) | What do we want to reflect upon? | Why are we asking this question? | What does success look like for this element? | What data will help us monitor this? | Within the data, what specific indicator will we use to monitor this? | When and how often will we monitor this? | Who is responsible for monitoring this? | Is there a starting point we want to compare the data with to monitor progress?
Activities
Mechanisms for Change
Enabling Factors
Outputs
Outcomes
Goals
Note: Goals beyond the accountability line are not included in the monitoring universe.

## 5. Data Sources
Data Sources
How will we measure it?
No. | Data Sources | Target Group | Owner
1 | Example: Online teacher survey | Teachers | Nancy
2
3
4
5
6
7
8
9